## Sheet1
TASK | START DATE | DURATION
Literature review | 2016-08-01 | 40
Generate initial dataset with fixed fibre arrangement | 2016-09-10 | 10
Generate initial model for predicting aggregate properies | 2016-09-20 | 20
Validate initial results using FE simulation | 2016-10-10 | 5
Quantification of Spatial Arrangement of Fibres | 2016-10-15 | 20
Generate data set by varying all parameters | 2016-12-01 | 90
Incorporate multiple particles and varying arrangement | 2017-03-01 | 30
Build robust model comprising all parameters | 2017-01-15 | 60
Make predictions and Validate using FE Simulations | 2017-02-15 | 30
Create Image-Processing model | 2017-03-15 | 30
Validate on data | 2017-04-01 | 15
Conclusion and Documentation | 2017-04-15 | 7