## Sheet1
Task | Start date | Days to complete
Literature review | 2016-08-01 | 40
Attribute Selection | 2016-09-10 | 20
Developing House of Quality | 2016-10-01 | 10
Preperation of questionnaire | 2016-10-10 | 21
Obtaining opinions of industry experts | 2016-11-01 | 60
Compilation of results and calulation of weights | 2017-01-01 | 45
Arriving at optimal QCs | 2017-02-15 | 15
Conclusion and documentation | 2017-03-01 | 30