## Sheet1
TASK | START DATE | DURATION
Literature review | 2016-08-01 | 40
Generate initial dataset with fixed particulate arrangement | 2016-09-10 | 10
Generate initial model for predicting aggregate properies | 2016-09-20 | 20
Validate initial results using FE simulation | 2016-10-10 | 5
Quantification of Structure Factor | 2016-10-15 | 20
Exploring the need of and defining Crowding Distance parameter | 2016-11-05 | 25
Generate comprehensive data set | 2016-12-01 | 60
Build robust model comprising all parameters | 2017-01-15 | 30
Make predictions on unknown materials for aggregate properties | 2017-02-15 | 15
Validate the results using FE simulation | 2017-03-01 | 15
Implement alternative definition of structure factor | 2017-03-15 | 15
Refine and tweak model | 2017-03-20 | 7
Create Image-Processing model | 2017-03-27 | 15
Define Inverse Optimization techniques | 2017-04-11 | 15
Evaluation and Summarising Results | 2017-04-25 | 7
| 2017-05-02 | 0